## Idea planner
TRAVEL WEBSITE PLANNER
TOPIC |  | PLAN DUE |  |  | KEYWORDS | NAME
UI/UX Graduation Project |  | 2025-03-22 |  |  | Innovative, fresh, elegant | Creative Crew
GOAL |  |  |  |  | OBJECTIVE
Engaging UI/UX experience with easy navigation, visually appealing design, and accessibility features for a seamless trip-planning journey. |  |  |  |  | Design a user-friendly family travel website that helps families plan trips efficiently.
| TASKS |  | START DATE | DEADLINE | DONE? | STATUS | CONTRIBUTERS
1 | Project idea discussion |  | 2025-12-26 | 2025-12-28 | Yes | 1 | entire team
1 | Survey questions planning |  | 2025-02-08 | 2025-02-21 | Yes | 1 | carol/youstina/sama/omnia
1 | Survey Form |  | 2025-03-03 | 2025-03-08 | Yes | 1 | habiba
1 | Progress sheet |  | 2025-03-22 | 2025-03-21 | Yes | 1 | habiba
1 | Define user personas |  | 2025-03-20 | 2025-03-21 | Yes | 1 | sama
-1 | Create User Flow diagrams |  | 376192 |  | Pending | -1
-1 | SWOT Analysis |  | 2202-12-22 |  | Pending | -1
| Low-Fidelity |  |  |  | No
| Style Guide |  |  |  | No
| Map User Journeys |  |  |  | No
| High-Fidelity |  |  |  | No
| Clickable Prototype |  |  |  | No
| Usability Testing |  |  |  | No
| Final Report |  |  |  | No
| Presentation |  |  |  | No
| Demo Video |  |  |  | No