## Idea planner
TRAVEL WEBSITE PLANNER
TOPIC |  | PLAN DUE |  |  | KEYWORDS | NAME
UI/UX Graduation Project |  | 2025-05-11 |  |  | Innovative, fresh, elegant | Creative Crew
GOAL |  |  |  |  | OBJECTIVE
Engaging UI/UX experience with easy navigation, visually appealing design, and accessibility features for a seamless trip-planning journey. |  |  |  |  | Design a user-friendly family travel website that helps families plan trips efficiently.
| TASKS |  | START DATE | DEADLINE | DONE? | STATUS | CONTRIBUTERS
1 | Project idea discussion |  | 2025-12-26 | 2025-12-28 | Yes | 1 | habiba,youstina,carol,sama,omnia
1 | Survey questions planning |  | 2025-02-08 | 2025-02-21 | Yes | 1 | carol/youstina/sama/omnia
1 | Final Survey PDF |  | 2025-02-09 | 2025-02-21 | Yes | 1 | carol
1 | Survey Form |  | 2025-03-03 | 2025-03-08 | Yes | 1 | habiba
1 | Progress sheet |  | 2025-03-22 | 2025-03-21 | Yes | 1 | habiba
1 | Research |  | 2025-03-20 |  | Yes | 1 | carol
1 | Stakeholder Interview |  | 2025-03-20 |  | Yes | 1 | youstina. omnia
1 | Define user personas |  | 2025-03-20 | 2025-03-21 | Yes | 1 | sama
1 | Empathy Map |  | 2025-03-20 |  | Yes | 1 | habiba
1 | User Analysis and Research |  | 2025-03-22 |  | Yes | 1 | habiba
1 | Create User Flow diagrams |  | 2025-04-04 |  | Yes | 1 | habiba,youstina,carol,sama,omnia
1 | Information Architecture |  | 2025-04-04 |  | Yes | 1 | habiba,youstina,carol,sama,omnia
1 | Competitor Analysis |  | 2025-03-22 |  | Yes | 1 | habiba
1 | SWOT Anlysis |  | 2025-03-22 |  | Yes | 1 | youstina,omnia,habiba
1 | Low-Fidelity |  | 2025-04-06 |  | Yes | 1 | youstina,carol.omnia
1 | Style Guide |  | 2025-04-11 |  | Yes | 1 | sama,habiba,omnia,carol,youstina
1 | Mid-Fidelity |  | 2025-04-08 | 09/042025 | Yes | 1 | sama,habiba,omnia,carol,youstina
1 | High-Fidelity |  | 2025-04-13 | 2025-04-25 | Yes | 1 | sama,habiba,omnia,carol,youstina
1 | Clickable Prototype |  | 2025-04-27 |  | Yes | 1 | sama,habiba,omnia,carol,youstina
1 | Usability Testing |  | 2025-05-02 |  | Yes | 1 | sama,habiba,omnia,carol,youstina
1 | Presentation |  | 2025-05-04 |  | Yes | 1 | sama,habiba,omnia,carol,youstina